# HUB ACTION PLAN

### Chair: Tian Barratt

### Vice-chair / Co-chair:  TBC

| Action | Outcomes and Outputs | Lead | Timescale | Update |
| --- | --- | --- | --- | --- |
| Student Facing |  |  |  |  |
| Increase provision/awareness of Creative Forces events in the region | Support stakeholders to set up and promote CF events – at least one new event | Tian | May 2026 | In progress: Bournemouth University looking to set secondary CF up |
|  | Capture CF best practice across Primary, Secondary and FE settings | Tian | Jul 2026 |  |
| Education Institutions/Teacher Facing |  |  |  |  |
| ## Develop a South Hub Creative Forces toolkit | Support HE practitioners in adopting the Creative Forces programme in their settings | TBC | Sept 27 |  |
| ## Host a regional conference to re-launch the South Hub | Set out a Hub vision and roadmap for 2025+ | Tian | February 2026 | In progress |
|  | Set out strategies for educator and student engagement (and respective working groups) | Tian | February 2026 | In progress |
|  | Provide CPD connected to the TLT, and school-improvement projects/case studies | Tian | February 2026 | In progress |
| ## Develop a Professional Development programme supporting school improvement in support for Service children | Establish hub working group led by Chair/Vice-chair to take this project forwards | TBC | Jan 26 – Sep 27 |  |
| Family Facing (Parents/Carers) |  |  |  |  |
| ## Develop a new tri-service families event | Establish hub working group led by a Vice-Chair to take this project forwards | TBC | July 2026 | In progress: ToC drafted |
| Research |  |  |  |  |
| Hub operation |  |  |  |  |
| Ensure all active hub members have read and signed membership documents | ToRs to be shared for review. All members to agree and sign membership documents to officially join/renew membership to the hub |  | January 2026 | In Progress: Draft ToR to be shared |
| Identify gaps in representation within the Hub and seek additional members to address these gaps | Carry out representation audit – identifying those who are currently not involved and considering how to engage with the hub | All | April 2026 | Not started: Linked to conference |
| Identify and appoint vice-chair(s) and agree term of service | Members to appoint based on individuals putting themselves forward |  | February 2026 | In progress |
| Explore collaboration with HEON | Bring HEON into the South Hub, or collaborate on cross-hub projects and approaches if HEON set up own hub |  | February 2026 | In progress |